## TestCase
Product Name |  | https://www.startech.com.bd/ | TC Start Date | 2023-08-09 | TC Execution Start Date | [5 empty] | TEST CASE
Module Name |  | Registration and login | TC End Date | 2023-08-10 | TC Execution End Date | [5 empty] | PASS | 27
Epic |  |  | Test Case Developed By | Mahin Ferdous | Browser (tested) | No |  |  |  |  | FAIL | 11
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | No |  |  |  |  | Not Executed | 0
Test Executed by | [10 empty] | Out of Scope | 0
[11 empty] | TOTAL | 38
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
2 | User Management | UI Testing | Registration | Verify the register link is visible or not | Link is visible | Found as per expectation | N/A | 1. Go to URL: https://www.startech.com.bd/ |  |  | Passed
3 |  |  |  | Verify the colour of register link by hovering | colour should be changed into orange by hovering | Found as per expectation | N/A | 1. Go to URL: https://www.startech.com.bd/ |  |  | Passed
4 |  |  |  | Verifying all the required field is marked with a red asterisk | Red asterisk should be present | Found as per expectation | N/A | 1. Go to URL: https://www.startech.com.bd/ |  |  | Passed
5 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Go to URL: https://www.startech.com.bd/ |  |  | Passed
6 |  |  |  | Verifying all the spelling and grammatical syntax | there should be no spelling and grammatical mistakes | Found as per expectation | N/A | 1. Go to URL: https://www.startech.com.bd/ |  |  | Passed
|  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1. Go to URL: https://www.startech.com.bd/ |  |  | Passed
10 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should be present | Found as per expectation | N/A | 1. Go to URL: https://www.startech.com.bd/ |  |  | Passed
11 |  | Functional Testing
12 |  |  |  | Verify that Keeping all the required fields blank | Should not allow user to register and show all the required error message | Found expected result along with an incorrect warning | N/A | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4.Keep required fields blank | Incorrect warning error |  | Failed
14 |  |  |  | Verify that first name and last name fields are case insensitive | Should accept the provided input | Found as per expectation | Firstname : maHin Lastname : FerDous | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4.Input case sensitive names in first and last name field 5. Fill up other fields 6.click "continue" |  |  | Passed
15 |  |  |  | Entering blank at first position in name field | Should not accept the provided input | not Found as per expectation |  | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4.Input case sensitive names in first and last name field 5. Fill up other fields 6.click "continue" | Blankspace error |  | Failed
16 |  |  |  | verify that Inputting name with only special characters | Should not accept the provided input with only special charater | Not found as per expectation | Firstname : @@@@@ @@@@@@ Lastname : &&&&&&&&&&&& | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4.Input special characters names in first and last name field 5. Fill up other fields 6.click "continue" | special character input |  | Failed
18 |  |  |  | verify that Inputing name field with only numbers | Should not accept the provided input with only number | Not found as per expectation | Firstname : 1234 Lastname : 5678 | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4. Enter numbers in name field 5.click the "continue" button | Numbers input error |  | Failed
19 |  |  |  | verify that Inputing name with alphanumeric characters | Should accept the provided input | Found as per expectation | Firstname : mahin66 Lastname : Ferdous12 | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4. Enter alphanumeric characters in name field 5.click the "continue" button |  |  | Passed
20 |  |  |  | Entering comma between alphabets in name | Should not accept the provided input including coma | Not found as per expectation | Firstname : mahin,66 Lastname : Ferdous,12 | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4. Enter alphanumeric characters with coma in name field 5.click the "continue" button | Coma in name error |  | Failed
21 |  |  |  | Validating an email id can only be used one time | Should not allow user to register and display a pop message | Found as per expectation with an error message | mahinferdousshoily@gmail.com | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4. Enter already registered email 5.click the "continue" button |  |  | Passed
23 |  |  |  | verify that incorrect email can not be used | Should not accept the provided email and display an error message | Found as not expectation | eee@@1111@hh>mgmail.com | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4. Enter invalid email 5.click the "continue" button | invalid email error |  | Failed
24 |  |  |  | verify that inputing valid email format | Should accept the provided input | Found as per expectation | mahinferdousshoily@gmail.com | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4. Enter a valid email 5.click the "continue" button |  |  | Passed
|  |  |  | verify blank input on telephone field | Should show required message | Found wrong warning |  | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4. Enter a valid name,email and keep telephone field blank 5.click the "continue" button | Wrong warning |  | Failed
|  |  |  | Verify invalid input on telephone field | Should show required message | Found as per expectation | 168433222 | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4. Enter a valid name,email and invalid inputtelephone field 5.click the "continue" button |  |  | Passed
|  |  |  | Verify that with all valid input for all field | Should let user countinue | Found as per expectation |  | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4. Enter a valid name,email and valid inputtelephone field 5.click the "continue" button |  |  | Passed
|  |  |  | Verify that user is getting OTP code after clicking continue with all valid input | Should provide an OTP code | Not found as per expectation |  | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4. Enter a valid name,email and valid inputtelephone field 5.click the "continue" button |  |  | Failed
25 |  |  |  | verify that Checking password and confirm field values are masked | Should be masked | Found as per expectation | mahin123 | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4. Enter a valid name,email and valid inputtelephone field 5.click the "continue" button 6. Enter same password for password and confirm password field |  |  | Passed
26 |  |  |  | Inputing invalid combinations of characters in password and confirm password field | Should not allow user to register and display a pop message | Found as per expectation | pass: 12345 confirm pass: 1234567 | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4. Enter a valid name,email and valid inputtelephone field 5.click the "continue" button 6. Enter different password for password and confirm password field . 7.click the "continue" button |  |  | Passed
27 |  |  |  | verify that Inputing password having length less then 4 | Should not allow password length less than 4 | Found as per expectation | 1111 | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4. Enter a valid name,email and valid inputtelephone field 5.click the "continue" button 6. Enter password valuew which is less then 4. 7.click the "continue" button |  |  | Passed
28 |  |  |  | verify that Inputing blank in password and confirm password field | Should not allow user to continue and display a required message | Found as per expectation | N/A | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button ""Account"" 3. Click the button ""Create your account"" 4. Enter a valid name,email and valid inputtelephone field 5.click the ""continue"" button 6. Keep passwordfield blank. 7.click the ""continue"" button" |  |  | Passed
29 |  |  |  | verify that Inputing strong password which has length between 4 to 20 | Should allow password length between 4 to 20. | Found as per expectation | mahin1234 | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4. Enter a valid name,email and valid inputtelephone field 5.click the "continue" button 6. Enter password value which has lenght between 4 to 20. 7.click the "continue" button |  |  | Passed
30 |  |  |  | Verify that Inputing different data for password and confirm password | Should not allow user and display a pop message | Found as per expectation | Password: mahi@8888 Confirm password: jnn8888 | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4. Enter a valid name,email and valid inputtelephone field 5.click the "continue" button 6. Enter different password for password and confirm password field . 7.click the "continue" button |  |  | Passed
31 |  |  |  | Verify that Inputing valid data for password and confirm password | Should allow user | Found as per expectation | Password: mahi@ Confirm password: mahi@ | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4. Enter a valid name,email and valid inputtelephone field 5.click the "continue" button 6. Enter different password for password and confirm password field . 7.click the "continue" button |  |  | Passed
32 |  |  |  | Verify that inputting password with lenght greater then 20 | Should not allow password length more then 20. | Found as per expectation | mahin1234567890132334 | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4. Enter a valid name,email and valid inputtelephone field 5.click the "continue" button 6. Enter password value which has lenght more then 20. 7.click the "continue" button |  |  | Passed
44 |  |  |  | Verify the "Back" button | User should be redirected to the previous page | Found as per expectation | N/A | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4.click the "Back" button |  |  | Passed
47
|  |  |  | Checking copy paste functionality in every field | Should copy and paste text from fields | Functioning successfully | mahin888 | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4. Copy paste text in every field |  |  | Passed
48 |  |  |  | Checking keyboard tab button functionality | Should switch to another field and highlight text | Not found as per expectation | Enter tab in every field | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4. Enter tab in every field |  |  | Failed
50
|  |  |  | verify that Keeping email and password fields blank | Should not allow user to login and displayrequired messeage | Not found as per expectation | N/A | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4. Click the button "Login". | required essage should be shown |  | Failed
51 |  |  |  | Checking if the data in password is masked | Should be masked | Found as per expectation | mahin## | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4. Click the button "Login". 3. Input value in password field and check if it is masked |  |  | Passed
52 |  | Functionality Testing | Log In | verify that login with only email | password should be requierd | Did not found as per expectetion | mahin@gmail.com | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4. Click the button "Login". 3. Input value in email field and keep password blank | password required message error |  | Failed
|  |  |  | verify that login wrong credentials in email and password field | Should not allow user to login and display an error messeage | Found as per expectation | name : Alex Password : Alx23 | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4. Click the button "Login". 3. Input value in email field and keep password blank |  |  | Passed
55 |  |  |  | Checking by selecting ‘Forgot Password’ | Account should be asked email/phone number | Found as per expectation | N/A | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click on the "forget password" button . |  |  | Passed
56 |  |  |  | Verify if password is visible or not | Should not be visible | Found as per expectation | N/A | 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4. Input value inpassword field |  |  | Passed
place captcha" for verifying human or robot
Place the check box "remember me" for remembering credentials
|  |  | Improvement Scopes | first name and last name should be placed onthe registration form

## MIndmaps
Mindmap for Startech.com website testing

## Bug Report
Bug Reporting | Bug Reporting | Bug Reporting
SL#12 Issue:Invalid warning message Reproducing Steps: 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4.Keep required fields blank Module: Registration Image : https://screenrec.com/share/HbM8mea7gV | SL#16 Issue: Inputting name with only special characters Reproducing Steps: 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4.Input special characters names in first and last name field 5. Fill up other fields 6.click "continue" Module: Registration Image : Special Character Error | SL#18 Issue: Registered with Inputing name with only numbers Reproducing Steps: 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4.Input only numbers in first and last name field 5. Fill up other fields 6.click "continue" Module: Registration Image : Number Error
Bug Reporting | Bug Reporting | Bug Reporting
SL#20 Issue: Entering comma between alphabets in name Reproducing Steps: 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4. Enter alphanumeric characters with coma in name field 5.click the "continue" button Module: Registration Image : Comma with Alphabets Error | SL#23 Issue: Registered with invalid email address Reproducing Steps: 1. Go to URL: https://www.startech.com.bd/ 2. Click the button "Account" 3. Click the button "Create your account" 4. Enter invalid email 5.click the "continue" button Module: Registration Image : invalid email error | SL# Issue: Reproducing Steps: Module: Log in Image :

## Report
Test Case Report
Project Name | startech.com
Module Name | Registration & Log in
Test Case Version
Written By | Mahin Ferdous
Executed By | Mahin ferdous
Reviewed By | Mahin ferdous
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 27 | 11 |  |  | 38
Grand Total | 27 | 11 | 0 | 0 | 38

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (38/38)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/38)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (27/39)*100 = 88
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (11/39)*100 = 12
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/50)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A